## Dashboard
Device Category | Number of Assets | Number of Compliant Assets | Percent Compliant
Firewall | 4 | 0 | 0%
Network Device | 20 | 20 | 100%
Server | 46 | 5 | 10.87%
PC Devices | 46 | 10 | 21.74%
Mobile Device | 100 | 1 | 1%
Cloud Service | 50 | 2 | 4%
Cyber Essentials Programme Tracker
Copyright Xservus Limited
Version 0.4
Date: 07/06/2022
Author: Daniel Card

## Progress Tracker
PERCENT COMPLIANT
Device Category | January | February | March | April | May | June | July | August | September | October | November | December
Firewall | 0 | 0 | 0 | 0 | 0 | 0 | 0
Network Device | 0 | 0 | 1 | 1 | 1 | 1 | 1
Server | 0 | 0 | 0.1087 | 0.1087 | 0.1087 | 0.1087 | 0.1087
PC Devices | 0 | 0 | 0.21739 | 0.21739 | 0.21739 | 0.21739 | 0.21739
Mobile Device | 0 | 0 | 0.01 | 0.01 | 0.01 | 0.01 | 0.01
Cloud Service | 0 | 0 | 0.04 | 0.04 | 0.04 | 0.04 | 0.04
SUM | 0 | 0 | 1.3761 | 1.3761 | 1.3761 | 1.3761 | 1.3761
Total Percent | 0% | 0% | 22.93% | 22.93% | 22.93% | 22.93% | 22.93%

## Project
Task ID | Task Name | Start Date | End Date | Task Owner | Task Members | Estiamted Effort (days) | Notes | Status
1 | Project Kick Off |  |  |  | Project Team | 2 |  | Not Started
2 | Planning |  |  |  | Project Team | 2 |  | Not Started
3 | Environment Asset Discovery |  |  |  | IT | 10 |  | Not Started
4 | Configuraiton Audits |  |  |  | IT | 10 |  | Not Started
5 | Process Audits |  |  |  | IT | 5 |  | Not Started
6 | Report & Review |  |  |  | Project Team | 5 |  | Not Started
7 | Remediation |  |  |  | IT | 20 |  | Not Started

## Remediation
Issue for Remediation | Description | Opened Date | Close Date | Owner | Estiamted Effort to Resolve | Notes | Status
Issue 1 | [6 empty] | In Progress
Issue 2 | [6 empty] | Complete

## Firewall
Device Name | OS Version | Build | Location | Owner | Warranty | Notes | OS Compliant & Suported by Vendor | Patched within 14 Days | In Support | Blocks Unused Services | Default Password Changed | Documented Config/Business Case | Rule Review Proces | Admin interface protected | Compliant
FW1 | PFSense | 2.6.0 | HQ | IT | N/A |  | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | TRUE | TRUE | FALSE
FW2 | PFSense | 2.6.0 | HQ | IT | N/A |  | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | TRUE | TRUE | FALSE
FW3 | PFSense | 2.6.0 | HQ | IT | N/A |  | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | TRUE | TRUE | FALSE
FW4 | PFSense | 2.6.0 | HQ | IT | N/A |  | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | TRUE | TRUE | FALSE

## DashData
Firewall Count | 4
Firewall Compliant | 0
Network Device Count | 20
Network Device Compliant | 20
Servers Count | 46
Servers Compliant | 5
PC Devices Count | 46
PC Devices Compliant | 10
Mobile Devices Count | 1
Mobile Devices Compliant | 1
Cloud Services Count | 2
Cloud Services Compliant | 2
Count of Issues | 2
Issues In Progress | 1
Issues Complete | 1

## Network Devices
Device Name | Device Type | Model | Firmware | Location | Owner | Warranty | Notes | OS Compliant & Suported by Vendor | Patched within 14 Days | Default Password Changed | Firmware Up to Date | Secure Configuration | Meets Standard
SWITCH1 | Netgear M4300-28G PoE+ | GSM4328PA | 12.0.17.7 | HQ | IT | Yes |  | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE
SWITCH2 | Netgear M4300-28G PoE+ | GSM4328PA | 12.0.17.8 | HQ | IT | Yes |  | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE
SWITCH3 | Netgear M4300-28G PoE+ | GSM4328PA | 12.0.17.9 | HQ | IT | Yes |  | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE
SWITCH4 | Netgear M4300-28G PoE+ | GSM4328PA | 12.0.17.10 | HQ | IT | Yes |  | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE
SWITCH5 | Netgear M4300-28G PoE+ | GSM4328PA | 12.0.17.11 | HQ | IT | Yes |  | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE
SWITCH6 | Netgear M4300-28G PoE+ | GSM4328PA | 12.0.17.12 | HQ | IT | Yes |  | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE
SWITCH7 | Netgear M4300-28G PoE+ | GSM4328PA | 12.0.17.13 | HQ | IT | Yes |  | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE
SWITCH8 | Netgear M4300-28G PoE+ | GSM4328PA | 12.0.17.14 | HQ | IT | Yes |  | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE
SWITCH9 | Netgear M4300-28G PoE+ | GSM4328PA | 12.0.17.15 | HQ | IT | Yes |  | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE
SWITCH10 | Netgear M4300-28G PoE+ | GSM4328PA | 12.0.17.16 | HQ | IT | Yes |  | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE
SWITCH11 | Netgear M4300-28G PoE+ | GSM4328PA | 12.0.17.17 | HQ | IT | Yes |  | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE
SWITCH12 | Netgear M4300-28G PoE+ | GSM4328PA | 12.0.17.18 | HQ | IT | Yes |  | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE
SWITCH13 | Netgear M4300-28G PoE+ | GSM4328PA | 12.0.17.19 | HQ | IT | Yes |  | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE
SWITCH14 | Netgear M4300-28G PoE+ | GSM4328PA | 12.0.17.20 | HQ | IT | Yes |  | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE
SWITCH15 | Netgear M4300-28G PoE+ | GSM4328PA | 12.0.17.21 | HQ | IT | Yes |  | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE
SWITCH16 | Netgear M4300-28G PoE+ | GSM4328PA | 12.0.17.22 | HQ | IT | Yes |  | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE
SWITCH17 | Netgear M4300-28G PoE+ | GSM4328PA | 12.0.17.23 | HQ | IT | Yes |  | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE
SWITCH18 | Netgear M4300-28G PoE+ | GSM4328PA | 12.0.17.24 | HQ | IT | Yes |  | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE
SWITCH19 | Netgear M4300-28G PoE+ | GSM4328PA | 12.0.17.25 | HQ | IT | Yes |  | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE
SWITCH20 | Netgear M4300-28G PoE+ | GSM4328PA | 12.0.17.26 | HQ | IT | Yes |  | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE

## Servers
Device Name | OS Version | Build | Role | Location | Owner | Warranty | Notes | OS Compliant & Suported by Vendor | Patched within 14 Days | Host Based Firewall Enabled | Dual Account Config | Account Lockout Policy | Account Password Polcy | Approved Software | Antimalware | Meets Standard
S1 | Windows Server 2022 | Version 10.0.14393 | [5 empty] | TRUE | TRUE | FALSE | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE
S2 | Windows Server 2022 | Version 10.0.14393 | [5 empty] | TRUE | TRUE | FALSE | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE
S3 | Windows Server 2022 | Version 10.0.14393 | [5 empty] | TRUE | TRUE | FALSE | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE
S4 | Windows Server 2022 | Version 10.0.14393 | [5 empty] | TRUE | TRUE | FALSE | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE
S5 | Windows Server 2022 | Version 10.0.14393 | [5 empty] | TRUE | TRUE | FALSE | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE
S6 | Windows Server 2022 | Version 10.0.14393 | [5 empty] | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE
S7 | Windows Server 2022 | Version 10.0.14393 | [5 empty] | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE
S8 | Windows Server 2022 | Version 10.0.14393 | [5 empty] | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | FALSE
S9 | Windows Server 2022 | Version 10.0.14393 | [5 empty] | TRUE | TRUE | TRUE | TRUE | FALSE | TRUE | TRUE | TRUE | FALSE
S10 | Windows Server 2022 | Version 10.0.14393 | [5 empty] | TRUE | TRUE | TRUE | TRUE | FALSE | TRUE | TRUE | TRUE | FALSE
S11 | Windows Server 2022 | Version 10.0.14393 | [5 empty] | TRUE | TRUE | TRUE | TRUE | FALSE | FALSE | TRUE | TRUE | FALSE
S12 | Windows Server 2022 | Version 10.0.14393 | [5 empty] | TRUE | TRUE | TRUE | TRUE | FALSE | TRUE | TRUE | TRUE | FALSE
S13 | Windows Server 2022 | Version 10.0.14393 | [5 empty] | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE
S14 | Windows Server 2022 | Version 10.0.14393 | [5 empty] | TRUE | TRUE | TRUE | TRUE | FALSE | TRUE | TRUE | TRUE | FALSE
S15 | Windows Server 2022 | Version 10.0.14393 | [5 empty] | TRUE | TRUE | TRUE | FALSE | FALSE | TRUE | FALSE | TRUE | FALSE
S16 | Windows Server 2022 | Version 10.0.14393 | [5 empty] | TRUE | TRUE | TRUE | TRUE | FALSE | TRUE | TRUE | TRUE | FALSE
S17 | Windows Server 2022 | Version 10.0.14393 | [5 empty] | TRUE | TRUE | TRUE | TRUE | FALSE | TRUE | TRUE | TRUE | FALSE
S18 | Windows Server 2022 | Version 10.0.14393 | [5 empty] | TRUE | TRUE | TRUE | TRUE | FALSE | FALSE | TRUE | TRUE | FALSE
S19 | Windows Server 2022 | Version 10.0.14393 | [5 empty] | TRUE | TRUE | TRUE | TRUE | FALSE | TRUE | TRUE | TRUE | FALSE
S20 | Windows Server 2022 | Version 10.0.14393 | [5 empty] | TRUE | TRUE | FALSE | TRUE | FALSE | TRUE | TRUE | TRUE | FALSE
S21 | Windows Server 2022 | Version 10.0.14393 | [5 empty] | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE
S22 | Windows Server 2022 | Version 10.0.14393 | [5 empty] | TRUE | TRUE | TRUE | TRUE | FALSE | TRUE | TRUE | TRUE | FALSE
S23 | Windows Server 2022 | Version 10.0.14393 | [5 empty] | TRUE | TRUE | TRUE | TRUE | FALSE | TRUE | TRUE | TRUE | FALSE
S24 | Windows Server 2022 | Version 10.0.14393 | [5 empty] | TRUE | TRUE | TRUE | TRUE | FALSE | TRUE | TRUE | TRUE | FALSE
S25 | Windows Server 2022 | Version 10.0.14393 | [5 empty] | TRUE | TRUE | TRUE | TRUE | FALSE | TRUE | TRUE | TRUE | FALSE
S26 | Windows Server 2022 | Version 10.0.14393 | [5 empty] | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE
S27 | Windows Server 2022 | Version 10.0.14393 | [5 empty] | TRUE | TRUE | FALSE | TRUE | FALSE | TRUE | TRUE | TRUE | FALSE
S28 | Windows Server 2022 | Version 10.0.14393 | [5 empty] | TRUE | TRUE | TRUE | TRUE | FALSE | FALSE | TRUE | TRUE | FALSE
S29 | Windows Server 2022 | Version 10.0.14393 | [5 empty] | TRUE | TRUE | TRUE | TRUE | FALSE | TRUE | TRUE | TRUE | FALSE
S30 | Windows Server 2022 | Version 10.0.14393 | [5 empty] | TRUE | TRUE | TRUE | TRUE | FALSE | TRUE | TRUE | TRUE | FALSE
S31 | Windows Server 2022 | Version 10.0.14393 | [5 empty] | TRUE | TRUE | TRUE | TRUE | FALSE | TRUE | TRUE | TRUE | FALSE
S32 | Windows Server 2022 | Version 10.0.14393 | [5 empty] | TRUE | TRUE | TRUE | TRUE | FALSE | TRUE | TRUE | TRUE | FALSE
S33 | Windows Server 2022 | Version 10.0.14393 | [5 empty] | TRUE | TRUE | TRUE | TRUE | FALSE | TRUE | FALSE | TRUE | FALSE
S34 | Windows Server 2022 | Version 10.0.14393 | [5 empty] | TRUE | TRUE | TRUE | TRUE | FALSE | TRUE | TRUE | TRUE | FALSE
S35 | Windows Server 2022 | Version 10.0.14393 | [5 empty] | TRUE | TRUE | FALSE | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE
S36 | Windows Server 2022 | Version 10.0.14393 | [5 empty] | TRUE | TRUE | TRUE | TRUE | FALSE | TRUE | TRUE | TRUE | FALSE
S37 | Windows Server 2022 | Version 10.0.14393 | [5 empty] | TRUE | TRUE | TRUE | TRUE | FALSE | TRUE | TRUE | TRUE | FALSE
S38 | Windows Server 2022 | Version 10.0.14393 | [5 empty] | TRUE | TRUE | TRUE | TRUE | FALSE | TRUE | FALSE | TRUE | FALSE
S39 | Windows Server 2022 | Version 10.0.14393 | [5 empty] | TRUE | TRUE | TRUE | TRUE | FALSE | TRUE | TRUE | TRUE | FALSE
S40 | Windows Server 2022 | Version 10.0.14393 | [5 empty] | TRUE | TRUE | TRUE | TRUE | FALSE | TRUE | TRUE | TRUE | FALSE
S41 | Windows Server 2022 | Version 10.0.14393 | [5 empty] | TRUE | TRUE | TRUE | TRUE | FALSE | TRUE | TRUE | TRUE | FALSE
S42 | Windows Server 2022 | Version 10.0.14393 | [5 empty] | TRUE | TRUE | FALSE | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE
S43 | Windows Server 2022 | Version 10.0.14393 | [5 empty] | TRUE | TRUE | TRUE | TRUE | FALSE | TRUE | TRUE | TRUE | FALSE
S44 | Windows Server 2022 | Version 10.0.14393 | [5 empty] | TRUE | TRUE | TRUE | TRUE | FALSE | TRUE | TRUE | TRUE | FALSE
S45 | Windows Server 2022 | Version 10.0.14393 | [5 empty] | TRUE | TRUE | TRUE | TRUE | FALSE | TRUE | TRUE | TRUE | FALSE
S46 | Windows Server 2022 | Version 10.0.14393 | [5 empty] | TRUE | FALSE | TRUE | TRUE | FALSE | TRUE | TRUE | TRUE | FALSE

## PC Devices
Device Name | OS Version | Build | Location | Owner | Warranty | Notes | OS Compliant & Suported by Vendor | Patched within 14 Days | Host Based Firewall Enabled | Dual Account Config | Account Lockout Policy | Account Password Polcy | Approved Software | Antimalware | Meets Standard
A1 | Windows 11 | Version 10.0.22000.708 |  |  |  |  | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE
A2 | Windows 11 | Version 10.0.22000.708 |  |  |  |  | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE
A3 | Windows 11 | Version 10.0.22000.708 |  |  |  |  | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE
A4 | Windows 11 | Version 10.0.22000.708 |  |  |  |  | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE
A5 | Windows 11 | Version 10.0.22000.708 |  |  |  |  | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE
A6 | Windows 11 | Version 10.0.22000.708 |  |  |  |  | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE
A7 | Windows 11 | Version 10.0.22000.708 |  |  |  |  | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE
A8 | Windows 11 | Version 10.0.22000.708 |  |  |  |  | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | FALSE
A9 | Windows 11 | Version 10.0.22000.708 |  |  |  |  | TRUE | TRUE | TRUE | TRUE | FALSE | TRUE | TRUE | TRUE | FALSE
A10 | Windows 11 | Version 10.0.22000.708 |  |  |  |  | TRUE | TRUE | TRUE | TRUE | FALSE | TRUE | TRUE | TRUE | FALSE
A11 | Windows 11 | Version 10.0.22000.708 |  |  |  |  | TRUE | TRUE | TRUE | TRUE | FALSE | FALSE | TRUE | TRUE | FALSE
A12 | Windows 11 | Version 10.0.22000.708 |  |  |  |  | TRUE | TRUE | TRUE | TRUE | FALSE | TRUE | TRUE | TRUE | FALSE
A13 | Windows 11 | Version 10.0.22000.708 |  |  |  |  | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE
A14 | Windows 11 | Version 10.0.22000.708 |  |  |  |  | TRUE | TRUE | TRUE | TRUE | FALSE | TRUE | TRUE | TRUE | FALSE
A15 | Windows 11 | Version 10.0.22000.708 |  |  |  |  | TRUE | TRUE | TRUE | FALSE | FALSE | TRUE | FALSE | TRUE | FALSE
A16 | Windows 11 | Version 10.0.22000.708 |  |  |  |  | TRUE | TRUE | TRUE | TRUE | FALSE | TRUE | TRUE | TRUE | FALSE
A17 | Windows 11 | Version 10.0.22000.708 |  |  |  |  | TRUE | TRUE | TRUE | TRUE | FALSE | TRUE | TRUE | TRUE | FALSE
A18 | Windows 11 | Version 10.0.22000.708 |  |  |  |  | TRUE | TRUE | TRUE | TRUE | FALSE | FALSE | TRUE | TRUE | FALSE
A19 | Windows 11 | Version 10.0.22000.708 |  |  |  |  | TRUE | TRUE | TRUE | TRUE | FALSE | TRUE | TRUE | TRUE | FALSE
A20 | Windows 11 | Version 10.0.22000.708 |  |  |  |  | TRUE | TRUE | FALSE | TRUE | FALSE | TRUE | TRUE | TRUE | FALSE
A21 | Windows 11 | Version 10.0.22000.708 |  |  |  |  | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE
A22 | Windows 11 | Version 10.0.22000.708 |  |  |  |  | TRUE | TRUE | TRUE | TRUE | FALSE | TRUE | TRUE | TRUE | FALSE
A23 | Windows 11 | Version 10.0.22000.708 |  |  |  |  | TRUE | TRUE | TRUE | TRUE | FALSE | TRUE | TRUE | TRUE | FALSE
A24 | Windows 11 | Version 10.0.22000.708 |  |  |  |  | TRUE | TRUE | TRUE | TRUE | FALSE | TRUE | TRUE | TRUE | FALSE
A25 | Windows 11 | Version 10.0.22000.708 |  |  |  |  | TRUE | TRUE | TRUE | TRUE | FALSE | TRUE | TRUE | TRUE | FALSE
A26 | Windows 11 | Version 10.0.22000.708 |  |  |  |  | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE
A27 | Windows 11 | Version 10.0.22000.708 |  |  |  |  | TRUE | TRUE | FALSE | TRUE | FALSE | TRUE | TRUE | TRUE | FALSE
A28 | Windows 11 | Version 10.0.22000.708 |  |  |  |  | TRUE | TRUE | TRUE | TRUE | FALSE | FALSE | TRUE | TRUE | FALSE
A29 | Windows 11 | Version 10.0.22000.708 |  |  |  |  | TRUE | TRUE | TRUE | TRUE | FALSE | TRUE | TRUE | TRUE | FALSE
A30 | Windows 11 | Version 10.0.22000.708 |  |  |  |  | TRUE | TRUE | TRUE | TRUE | FALSE | TRUE | TRUE | TRUE | FALSE
A31 | Windows 11 | Version 10.0.22000.708 |  |  |  |  | TRUE | TRUE | TRUE | TRUE | FALSE | TRUE | TRUE | TRUE | FALSE
A32 | Windows 11 | Version 10.0.22000.708 |  |  |  |  | TRUE | TRUE | TRUE | TRUE | FALSE | TRUE | TRUE | TRUE | FALSE
A33 | Windows 11 | Version 10.0.22000.708 |  |  |  |  | TRUE | TRUE | TRUE | TRUE | FALSE | TRUE | FALSE | TRUE | FALSE
A34 | Windows 11 | Version 10.0.22000.708 |  |  |  |  | TRUE | TRUE | TRUE | TRUE | FALSE | TRUE | TRUE | TRUE | FALSE
A35 | Windows 11 | Version 10.0.22000.708 |  |  |  |  | TRUE | TRUE | FALSE | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE
A36 | Windows 11 | Version 10.0.22000.708 |  |  |  |  | TRUE | TRUE | TRUE | TRUE | FALSE | TRUE | TRUE | TRUE | FALSE
A37 | Windows 11 | Version 10.0.22000.708 |  |  |  |  | TRUE | TRUE | TRUE | TRUE | FALSE | TRUE | TRUE | TRUE | FALSE
A38 | Windows 11 | Version 10.0.22000.708 |  |  |  |  | TRUE | TRUE | TRUE | TRUE | FALSE | TRUE | FALSE | TRUE | FALSE
A39 | Windows 11 | Version 10.0.22000.708 |  |  |  |  | TRUE | TRUE | TRUE | TRUE | FALSE | TRUE | TRUE | TRUE | FALSE
A40 | Windows 11 | Version 10.0.22000.708 |  |  |  |  | TRUE | TRUE | TRUE | TRUE | FALSE | TRUE | TRUE | TRUE | FALSE
A41 | Windows 11 | Version 10.0.22000.708 |  |  |  |  | TRUE | TRUE | TRUE | TRUE | FALSE | TRUE | TRUE | TRUE | FALSE
A42 | Windows 11 | Version 10.0.22000.708 |  |  |  |  | TRUE | TRUE | FALSE | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE
A43 | Windows 11 | Version 10.0.22000.708 |  |  |  |  | TRUE | TRUE | TRUE | TRUE | FALSE | TRUE | TRUE | TRUE | FALSE
A44 | Windows 11 | Version 10.0.22000.708 |  |  |  |  | TRUE | TRUE | TRUE | TRUE | FALSE | TRUE | TRUE | TRUE | FALSE
A45 | Windows 11 | Version 10.0.22000.708 |  |  |  |  | TRUE | TRUE | TRUE | TRUE | FALSE | TRUE | TRUE | TRUE | FALSE
A46 | Windows 11 | Version 10.0.22000.708 |  |  |  |  | TRUE | FALSE | TRUE | TRUE | FALSE | TRUE | TRUE | TRUE | FALSE

## Mobile Devices
Device Name | OS Version | Build | Location | Owner | Warranty | Notes | OS Compliant & Suported by Vendor | AutoLock | Not Jail Broken | Patched within 14 Days | Device Unlock Feature in use (e.g. PIN or BIOMETRICS) | Approved Software Only | Remote Wipe Possible | Meets Standard
M1 | IOS | 15 |  |  |  |  | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE

## Cloud Services
Service Name | Provider | Location | Owner | Notes | Password Polcy Meets Standards | Account Lockouts Enabled | Multifactor Authentication for All Users | Meets Standard
Azure | Microsoft |  |  |  | TRUE | TRUE | TRUE | TRUE
Office 365 | Microsoft |  |  |  | TRUE | TRUE | TRUE | TRUE